## Project Schedule
PROJECT SCHEDULE
PROJECT NAME |  |  |  | START DATE
Multi-Player BlackJack Game |  |  |  | 2022-06-13
PROJECT MEMBER |  |  |  | END DATE
Daniel Jensen, Chun Yin Lee, Aastha Sharma |  |  |  | 2022-07-27
| TIMELINE |  |  | PROJECT NOTES
PHASE TITLE | START DATE | END DATE | DURATION in days | ISSUES | COMMENTS
Requirement | 2022-06-13 | 2022-06-19 | 7 | n/a | Software_Requirements_Specification.docx
Design | 2022-06-20 | 2022-07-17 | 28 | n/a | Design_Specification_Document.docx
Implementation | 2022-07-18 | 2022-07-24 | 7 | can't complete
Testing and Maintence | 2022-07-25 | 2022-07-27 | 3 | n/a | 9 Junit tests
Presentation day | 2022-07-27 | 2022-07-27 | 1
DELIVERY TIMELINE